## Sheet1
Week |  | Work
|  | Task 1 | Completed | Task 2 | Completed | Extra task | Completed
2019-03-25 |  | Translate Python code to Javascript |  | Link all web pages together | Complete | Get buttons on web pages to be able to send data to script | Complete
2019-04-01 |  | Translate Python code to Javascript | Complete | Get buttons on web pages to be able to send data to script |  | Prepare presentation and write documentation, basic operation, and algorithm info | Complete
2019-04-08 |  | Put script and buttons together and make first stable release |  | Get buttons on web pages to be able to send data to script | Complete | Write documentation, basic operation, and algorithm info | Complete
2019-04-15 |  | Put script and buttons together and make first stable release | Complete | Make three preset configurations for the user to select ahead of time |  | Continue editing the layout of the homepage | Complete
2019-04-22 | TBD | Figure out how to save the users saved data |  | Make three preset configurations for the user to select ahead of time |  | Prepare presentation for tri-weekly report
2019-04-29 | TBD
2019-05-06 | TBD | Final Presentation Prep
2019-05-13 | TBD | Final Presentation Prep
2019-05-20 | TBD